RepRush

Gamified Fitness Tracker

Document 6: Task Breakdown & Development Roadmap

10-Day MVP Sprint Plan v1.0

Version 1.0  |  April 2026  |  Confidential

# Roadmap Philosophy

Every milestone ends with a fully demo-able app. No milestone ends with a broken screen, a placeholder, or an unfinished flow. If a feature is not completed within a milestone, it is deferred to the next — never shipped half-built.

The roadmap is structured for a 2-person team with a 10-day MVP deadline. The critical path runs through the workout logging flow (Days 1-5). Social and analytics features are built on top of a stable core.

# Milestone 1 — Foundation (Day 1)

## Goal

The project builds, Firebase is connected, Google login works end-to-end, and the Room database schema is fully defined with no placeholder tables.

## Tasks

- Create Android project with Kotlin. Set up Material 3 XML theme (Theme.Material3.DayNight) in themes.xml and colors.xml.

- Add all Gradle dependencies: Firebase BOM, Room with KSP annotation processor, Jetpack Navigation Component, MPAndroidChart, ViewBinding enabled in build.gradle.

- Set up Firebase project: enable Authentication (Google provider), enable Firestore, download google-services.json.

- Enable Firestore offline persistence in Application class.

- Define full Room database schema: all 11 entity data classes, all DAO interfaces (method signatures only), and the AppDatabase class with version 1.

- Implement Google Sign-In using Firebase Auth SDK. Handle success (navigate to onboarding or home), failure (show Snackbar), and already-signed-in (skip to home).

- Implement onboarding questionnaire: 5 Fragments with back/next navigation using NavController, input validation, save to Room and Firestore on completion.

- Set up Navigation graph (nav_graph.xml) with all Fragment destinations defined. Non-entry destinations can use placeholder layouts at this stage.

## Demo State at End of Milestone 1

App opens to a Google Sign-In screen. Signing in with a Google account creates a user profile. Completing the onboarding questionnaire saves the profile and navigates to a placeholder Home screen. On re-launch, the user is already logged in and goes directly to Home.

## Deliberately Left Out

No workout features, no exercise library, no UI polish. The sole focus is a solid, working foundation.

# Milestone 2 — Exercise Library & AI Plan Import (Days 2-3)

## Goal

Users can browse exercises and import a full AI-generated workout plan that is saved and viewable.

## Tasks — Day 2

- Create Room seed data: 80 exercises as a pre-populated list inserted via RoomDatabase.Callback on first create.

- Build ExerciseLibraryFragment: RecyclerView with search EditText and Material Chip filter row. Implement search and filter logic in ViewModel using LiveData.

- Build ExerciseDetailFragment: shows name, muscles, equipment. Shows No history yet for chart and PR sections.

- Build AddCustomExerciseFragment: form with name, muscle group, equipment, category fields and save button. Validate for duplicate names.

## Tasks — Day 3

- Build AI questionnaire flow: 8-step Fragment using ViewPager2 or sequential navigation. Pre-fill from user profile. All inputs validated before proceeding.

- Build PromptGenerator class: takes questionnaire answers and returns the full prompt string.

- Build prompt display Fragment: ScrollView with prompt text, copy-to-clipboard button, Next: Paste Response button.

- Build JSON paste Fragment: multiline EditText, Import Plan button.

- Build PlanImportValidator: validates all fields, returns typed error list or success. Schema version check first.

- Build PlanImportRepository function: parses valid JSON, cross-references exercises, auto-creates unknowns, writes to Room across all 3 plan tables in a transaction.

- Build PlanSummaryFragment: shows imported plan with expandable RecyclerView day list, rename EditText, Set as Active button.

- Build PlanListFragment: RecyclerView of all saved plans, active badge, switch and delete via item touch or context menu.

## Demo State at End of Milestone 2

User can browse and search all 80 exercises. They can add a custom exercise. They can complete the AI questionnaire, copy the generated prompt, paste a valid AI JSON response, and see the import succeed with a plan summary. The plan is visible in a list and can be set as active.

# Milestone 3 — Workout Logging (Day 4)

## Goal

Users can log a complete workout session — starting from a plan or blank, adding sets, marking warmups, using the rest timer, and finishing the session.

## Tasks

- Build ActiveSessionFragment: top Toolbar with elapsed timer, NestedScrollView containing exercise cards, FAB to add exercise, Finish button.

- Build ExerciseCardView: custom ViewGroup or ConstraintLayout-based layout, collapsed/expanded state, set rows with weight/reps EditText and checkmark, Add Set button, warmup toggle per set.

- Implement SessionViewModel: manages in-memory session state using LiveData, does NOT write to Room until Finish is confirmed.

- Build rest timer: CountDownTimer, foreground Service with notification showing countdown and +30s and Skip action buttons.

- Implement Start from plan flow: load today's plan_day exercises via Room query and pre-populate the session.

- Implement Start empty flow: open session with no exercises, user adds from library via bottom sheet.

- Build FinishWorkoutFragment: shows session summary (duration, sets, volume). Confirm button triggers save.

- Implement session save transaction: write workout_session and all logged_sets to Room.

## Demo State at End of Milestone 3

User can start today's workout from the Home screen, see all exercises pre-loaded, log sets with weight and reps, mark warmups, use the rest timer with screen off, add extra exercises, and finish the session to see a summary. All data saved to Room.

# Milestone 4 — Gamification (Days 5-6)

## Goal

Every completed workout awards points, detects PRs, updates streaks, and checks achievements. The post-workout celebration screen is polished and motivating.

## Tasks — Day 5

- Implement PointsCalculator: pure Kotlin class, all point rules as named constants, daily cap logic, streak bonus logic.

- Implement PRDetector: on session save, query Room for historical max weight per exercise per rep count, identify new records.

- Implement PRRecordRepository: update pr_records table, mark isPersonalRecord on the logged_set.

- Integrate points and PR detection into session finish flow: calculate points, detect PRs, update streak, then write session.

- Implement streak logic: compare lastWorkoutDate against today and the plan schedule, increment or reset streak.

- Update streaks table in Room and users document in Firestore after every session.

## Tasks — Day 6

- Build AchievementChecker: checks all 11 badge conditions after every session and on app open.

- Build PostWorkoutFragment: points breakdown CardView, PR cards in RecyclerView with exercise name and weight, achievement unlock cards.

- Add Material Motion animation on PR card entrance using MaterialFadeThrough or spring-based ObjectAnimator.

- Build GlobalLeaderboardFragment: Firestore real-time listener for current month, RecyclerView with rank/avatar/name/points, user's own row pinned.

- Write Firestore leaderboard update in session finish flow: transaction on leaderboard/{month}/{uid}.

- Update Home dashboard with real data: streak count, monthly points, rank.

## Demo State at End of Milestone 4

Completing a workout shows a celebration screen with points breakdown and any new PRs. The Home dashboard shows a live streak counter and monthly point total. The global leaderboard shows real user data from Firestore.

# Milestone 5 — Progress & Analytics (Day 7)

## Goal

The Progress tab is complete with history calendar, per-exercise charts, body weight tracking, strength score, and volume trend.

## Tasks

- Build HistoryFragment: custom calendar View with color-coded days (completed/missed/rest) drawn on a GridLayout or custom Canvas View.

- Build WorkoutHistoryListFragment: RecyclerView of past sessions with date, duration, volume, points.

- Build SessionDetailFragment: all exercises and sets for a past session with warmup and PR badges.

- Build per-exercise progress chart in ExerciseDetailFragment: MPAndroidChart LineChart with max weight over time.

- Build WeeklyVolumeChart: MPAndroidChart BarChart for sets per muscle group in the current week.

- Build BodyWeightFragment: EditText log entry, MPAndroidChart LineChart with rolling average overlay, stats TextViews.

- Build StrengthScoreFragment: computed score TextView, level label, MPAndroidChart LineChart for score history.

- Build PerLiftTrendSection: 5 CardViews with current 1RM, 30-day change delta, and small sparkline chart.

- Build TotalVolumeTrendFragment: MPAndroidChart BarChart for 12 weeks of total weekly volume.

## Demo State at End of Milestone 5

The Progress tab is fully functional. User can view workout history as a calendar and list, inspect past sessions, see per-exercise strength charts, track body weight over time, and see their overall strength score and volume trend.

# Milestone 6 — Social & Profile (Day 8)

## Goal

Friend system, private groups, and profile screen are complete and backed by real Firestore data.

## Tasks

- Build FriendSearchFragment: EditText search by display name, Firestore query, send request button.

- Build FriendRequestsFragment: RecyclerView of incoming requests with accept/decline buttons.

- Implement Firestore friend request model: write to friendRequests/{uid}/incoming and outgoing.

- Build FriendsListFragment: RecyclerView of accepted mutual friends.

- Build CreateGroupFragment: name EditText, member selector from friends list using RecyclerView with checkboxes.

- Build GroupDetailFragment: group info, member RecyclerView with all-time points and leaderboard ranking.

- Build ProfileFragment: CircleImageView avatar, display name, stats summary CardViews, achievements GridLayout.

- Implement all-time stats computation from Room: total workouts, total PRs, total volume, longest streak.

## Demo State at End of Milestone 6

User can send friend requests, accept them, create a private group, invite friends, and view a group leaderboard. The profile screen shows all stats and unlocked achievements.

# Milestone 7 — Polish & Demo Prep (Days 9-10)

## Goal

The app is visually polished, handles all edge cases and error states, and is loaded with realistic demo data for the teacher presentation.

## Tasks — Day 9

- Audit all screens for empty states: every RecyclerView and chart has a designed empty state with an icon TextView and call-to-action Button.

- Audit all screens for loading states: Firestore queries and Room queries show a ProgressBar.

- Audit all screens for error states: network errors show a Snackbar with retry, validation errors are specific and shown inline.

- Apply consistent Material Motion: Activity/Fragment transitions using MaterialFadeThrough and MaterialSharedAxis.

- Implement Settings Fragment: rest timer default SeekBar, auto-timer toggle Switch, weight unit RadioGroup, leaderboard opt-in Switch, sign out Button.

- Add contentDescription to all ImageViews and IconButtons for TalkBack support.

- Test light mode and dark mode on all screens using the day/night theme switch.

## Tasks — Day 10

- Seed the demo account with realistic data: 4 weeks of workout history, multiple PRs across 5 exercises, a 14-day streak, 6 achievement badges unlocked.

- Test the full AI import flow with a real ChatGPT and real Gemini response. Verify parsing works for both.

- Test offline behavior: disable WiFi, log a workout, re-enable WiFi, verify Firestore sync.

- Test on a physical device for real-world performance and scroll smoothness.

- Prepare demo script: Home -> Start Today's Workout -> Log 3 sets -> Finish -> Celebration -> PR -> Leaderboard -> Progress tab -> Body weight chart -> Strength score -> AI Plan generation.

- Fix any crash or regression found during demo testing.

## Demo State at End of Milestone 7

A fully polished, data-rich app that demonstrates all core flows without any placeholder content, loading failures, or crashes. Ready for a live teacher demonstration.